| Research Terms of Reference Education Sector Assessment BGD2006 Cox’s Bazar District, Bangladesh |  |
| --- | --- |
| August 2020 V 1.0 |  |

# Executive Summary

| Country of intervention | Bangladesh |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Emergency | □ | Natural disaster | X | Conflict |  |  |  |  |  |
| Type of Crisis | □ | Sudden onset | □ | Slow onset |  |  | X | Protracted |  |
| Mandating Body/ Agency | UNICEF |  |  |  |  |  |  |  |
| Project Code | 70EAD |  |  |  |  |  |  |  |
| Overall Research Timeframe (from research design to final outputs / M&E) | 27/07/2020 to 31/12/2020 |  |  |  |  |  |  |  |
| Research Timeframe | 1. Start collect data: 15/10/2020 |  |  |  | 5. Preliminary presentation: 04/01/2021 |  |  |  |
| Add planned deadlines (for first cycle if more than 1) | 2. Data collected: 30/11/2020 |  |  |  | 6. Outputs sent for validation: 17/01/2021 |  |  |  |
|  | 3. Data analysed: 14/12/2020 |  |  |  | 7. Outputs published: 28/02/2021 |  |  |  |
|  | 4. Data sent for validation: 14/12/2020 |  |  |  | 8. Final presentation: N/A |  |  |  |
| Number of assessments | X | Single assessment (one cycle) |  |  |  |  |  |  |
|  | □ | Multi assessment (more than one cycle) [Describe here the frequency of the cycle] |  |  |  |  |  |  |
| Humanitarian milestones Specify what will the assessment inform and when e.g. The shelter cluster will use this data to draft its Revised Flash Appeal; | Milestone |  |  |  | Deadline |  |  |  |
|  | □ | Donor plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | X | Inter-cluster plan/strategy |  |  | 31/01/2021 |  |  |  |
|  | X | Sector plan/strategy |  |  | 31/01/2021 |  |  |  |
|  | □ | NGO platform plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | □ | Other (Specify): |  |  | _ _/_ _/_ _ _ _ |  |  |  |
| Audience Type & Dissemination Specify who will the assessment inform and how you will disseminate to inform the audience | Audience type |  |  |  | Dissemination |  |  |  |
|  | X Strategic X Programmatic □ Operational □ [Other, Specify] |  |  |  | □ General Product Mailing (e.g. mail to NGO consortium; HCT participants; Donors) □ Cluster Mailing (Education, Shelter and WASH) and presentation of findings at next cluster meeting □ Presentation of findings (e.g. at HCT meeting; Cluster meeting) X Website Dissemination (Relief Web & REACH Resource Centre) □ [Other, Specify] |  |  |  |
| Detailed dissemination plan required | □ | Yes |  |  | X | No |  |  |
| General Objective | To support UNICEF and the Cox’s Bazar Education Sector to understand the effectiveness and challenges of the education response within host communities (HC) and in camps, and to guide their future response by ensuring equitable and quality education opportunities for all children/youths aged 3-2424. |  |  |  |  |  |  |  |
| Specific Objective(s) | 1. Assess the effectiveness of the Education in Emergencies (EiE) response and the impact on learning outcomes, including the Learning Competency Framework and Approach (LCFA) developed in camps. 2. Assess the challenges, bottlenecks, and constraints on learning for Rohingya-refugee and HC children/youths aged 3-24. 3. Jointly with Education partners, identify areas for improvement, good practices, lessons learned of the EiE response for all children/youths aged 3-24. 4. Assess to what extent has COVID-19 affected the learning of Rohingya and HC children/youths aged 3-24 |  |  |  |  |  |  |  |
| Research Questions | - RQ1.1: How effective was the Education Sector’s response in the past year in camps and in HC? - To what extent has the provision of learning spaces and infrastructure contributed to improved access to education services for children/youths aged 3 to 24 through an equity lens? - To what extent has the provision of education materials and community sensitization efforts contributed to improved access to education services for children/youths aged 3 to 24 through an equity lens? - RQ1.2: Are the INEE minimum standards for teacher recruitment and remuneration being consistently followed by all sector partners? If not, why? - RQ1.3: What are the lessons learned of the LCFA on learning outcomes? - RQ2.1: To what extent are the Education Sector and Partners ensuring access to equitable learning opportunities in a safe and protective environment for children/youths aged 3-24, including children/youths with disabilities and non-binary gender identities? - RQ3.2: What are the improvements, good practices and recommendations that could guide the future of the Education Sector response and ensure equitable and quality education opportunities? - RQ4.1: How have children/youths aged 3-24 been able to continue learning since COVID-19? - RQ4.2: What were the barriers to providing children/youths aged 3-24 with education during COVID-19 and what are the lessons learned? - How should the Education Sector involve educators in supporting children/youths during COVID-19? |  |  |  |  |  |  |  |
| Geographic Coverage | Teknaf and Ukhiya upazilas (HC and refugees’ camps) |  |  |  |  |  |  |  |
| Secondary data sources | - Report on the pilot test of the Annual Status Of Education Report (ASER), BRAC; August 2018 - Preliminary Results ASER Plus, Cox’s Bazar Education Sector; February 2019 - Overview of the ASER-PLUS assessment for refugee students, Cox’s Bazar Education Sector; April 2019 - Report on the ASER tests 2019 - ISCG Facility Mapping Data on educational facilities - Education Sector 5W - MICS (Multiple Indicator Cluster Survey) 2019 - Annual Primary School Census 2019 |  |  |  |  |  |  |  |
| Population(s) | □ | IDPs in camp |  |  | □ | IDPs in informal sites |  |  |
| Select all that apply | □ | IDPs in host communities |  |  | □ | IDPs [Other, Specify] |  |  |
|  | X | Refugees in camp |  |  | □ | Refugees in informal sites |  |  |
|  | □ | Refugees in host communities |  |  | □ | Refugees [Other, Specify] |  |  |
|  | X | Host communities |  |  | □ | [Other, Specify] |  |  |
| Stratification Select type(s) and enter number of strata | X | Geographical #: 2 upazilas (Ukhiya and Teknaf) Population size per strata is known? X Yes □ No | X | Group #: Refugees and HC Population size per strata is known? X Yes □ No |  |  | □ | [Other Specify] #: _ _ Population size per strata is known? □ Yes □ No |
| Data collection tool(s) | X | Structured (Quantitative) |  |  | X | Semi-structured (Qualitative) |  |  |
|  | Sampling method |  |  |  | Data collection method |  |  |  |
| Structured data collection tool # 1 Rohingya and Bangladeshi caregivers | □ Purposive X Probability / Simple random □ Probability / Stratified simple random □ Probability / Cluster sampling □ Probability / Stratified cluster sampling □ [Other, Specify] |  |  |  | □ Key informant interview (Target #):_ _ _ _ _ □ Group discussion (Target #):_ _ _ _ _ X Household interview (Target #): 200 with Rohingya caregivers and 2002 with Bangladeshi caregivers, at a 95% level of confidence with a +/- 10% margin of error at the Upazila and demographic group-level, and 95% level of confidence with a +/- 7% margin of error at the response-level □ Individual interview (Target #):_ _ _ _ _ □ Direct observations (Target #):_ _ _ _ _ □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Structured data collection tool # 2 Bangladeshi teachers (HC), Bangladeshi teachers (camps) and Burmese language instructors (camps) | □ Purposive X Probability / Simple random □ Probability / Stratified simple random □ Probability / Cluster sampling □ Probability / Stratified cluster sampling □ [Other, Specify] |  |  |  | □ Key informant interview (Target #):_ _ _ _ _ □ Group discussion (Target #):_ _ _ _ _ X Individual interview (Target #): 2002 with Bangladeshi teachers in HC, 2002 with Bangladeshi teachers in camps and 2002 with Burmese language instructors in camps at a 95% level of confidence with a +/- 10% margin of error at the demographic group level □ Direct observations (Target #):_ _ _ _ _ □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Semi-structured data collection tool #1 Focus group discussions (FGDs) | X Purposive □ Snowballing □ [Other, Specify] |  |  |  | □ Key informant interview (Target #):_ _ _ _ _ □ Individual interview (Target #):_ _ _ _ _ X Focus group discussion (Target #): 20 FGDs made up of Bangladeshi caregivers, Rohingya caregivers, caregivers of children/youths with special needs, children/youths aged 12-24. □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Semi-structured data collection tool #2 Key informant interviews (KIIs) | X Purposive □ Snowballing □ [Other, Specify] |  |  |  | X Key informant interview (Target #): 20 KIIs from a combination of CBOs supporting vulnerable or marginalised children/youths, Education NGO implementing partners, members of Learning Centre Management Committees. □ Individual interview (Target #):_ _ _ _ _ □ Focus group discussion (Target #): □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Target level of precision if probability sampling | 95% level of confidence |  |  |  | +/- 10% margin of error at Upazila-level and demographic group-level; +/- 7% margin of error at the response-level |  |  |  |
| Data management platform(s) | X | IMPACT |  |  | □ | UNHCR |  |  |
|  | □ | [Other, Specify] |  |  |  |  |  |  |
| Expected ouput type(s) | □ | Situation overview #: _ _ | X | Report #: 1 Either a single full-length synthesized report, or multiple analytical and thematic briefs accompanied by a synthesized executive summary. |  |  | □ | Profile #: _ _ |
|  | X | Presentation (Preliminary findings) #: 2 | □ | Presentation (Final) #: _ _ |  |  | □ | Factsheet #: |
|  | □ | Interactive dashboard #:_ | □ | Webmap #: _ _ |  |  | □ | Map #: _ _ |
|  | □ | [Other, Specify] #: _ _ |  |  |  |  |  |  |
| Access | X | Public (available on REACH resource center and other humanitarian platforms) |  |  |  |  |  |  |
|  | □ | Restricted (bilateral dissemination only upon agreed dissemination list, no publication on REACH or other platforms) |  |  |  |  |  |  |
| Visibility Specify which logos should be on outputs | REACH |  |  |  |  |  |  |  |
|  | Donor: UNICEF |  |  |  |  |  |  |  |
|  | Coordination Framework: Education Sector |  |  |  |  |  |  |  |
|  | Partners: Education Sector (Save The Children, NRC, Plan International, BRAC, VSO…) |  |  |  |  |  |  |  |

# Rationale

Since August 2017, an estimated 745,000 Rohingya refugees have arrived in Bangladesh’s Cox’s Bazar District fleeing military operations characterized by widespread reports of human rights violations in Myanmar. Currently, there are over 900,000 Rohingya refugees living in 34 settlements in Ukhiya and Teknaf, and of these, 55% are children. Stripped of the citizenship by the Myanmar state, refugees have left an environment in Myanmar in which access to basic services—including education— was severely limited. Reportedly, less than 60% of children arriving in Bangladesh have ever attended school in Myanmar, while less than one-tenth graduated beyond primary level.

Cox’s Bazar is one of the most impoverished districts of Bangladesh. The primary school completion rate for the district is 54%, while the divisional and countrywide rate is closer to 80%. Findings from the recent Joint MSNA in October 2019 may point to a slight improvement with roughly 70% of primary school-aged children (aged 5-11) and 64% of secondary school-aged children (12-17) reported to be enrolled in a formal education programme (e.g. government schools, Alia madrassas) at the time of data collection. Regarding non-formal educational opportunities, across all 11 assessed Unions, reported attendance of NGO-run schools was seemingly low, with fewer than 10% of children reporting to access these learning modalities in any given Union.

Over the course of the past two and a half years, education providers have made significant inroads into providing an education system to serve over half a million children, with over 5,000 facilities and almost 65-70% of boys and girls aged 3-5 and 6-24 reportedly attending learning spaces as of March 2019., However, significant challenges remain. Attendance rates of adolescents, particularly adolescent girls, remain extremely limited. Particular challenges persist for children with disabilities, who were reported to be attending learning centres at lower rates than their peers for all age ranges. Limited space in crowded camps mean that partners have had to employ alternative modalities to fully-subscribed learning spaces in order to reach additional children. Within the HC, the main barriers to education were economic, with 34% of households reporting that the cost of education was too high; 32% reporting that the child is needed to contribute to household income; and 26% reporting that the child was needed to help out around the home.4

However, access is only one component of a holistic approach to the larger framework ensuring the right to education for all girls and boys. Key information gaps continue to persist regarding the quality of educational opportunities, from the perspective of both service providers and the household users and within the framework of learning outcomes, portable skills, and competencies. Additionally, overarching accountability principles such as community engagement, participation, satisfaction, and empowerment within children’s education – all components that should serve to improve and enrich children’s experiences – are not always taken up within the HC or refugee population groups. The roll-out of the alternative Learning Competencies Framework and Approach (LCFA) in 2019 provided a key opportunity to emphasize and incorporate parent and community engagement and preferences regarding different learning modality options. The proposed assessment therefore aims to build upon the initial groundwork and community consultations and to provide a robust evidence base one-year into its implementation regarding best practices and recommended course corrections, from the perspectives of households and caregivers, service providers, programmatic stakeholders, and community members. This assessment also aims to identify how COVID-19 has affected learning opportunities for children. It will be looking at the most common modalities of distance learning that are being used by educators and assessing how educators should be more involved in supporting children during COVID-19.

Following the global outbreak of COVID-19, the government of Bangladesh adopted various measures aimed at controlling the spread of the disease, with schools closing nationwide on March 18. To support the continuity of educational opportunities, the Ministry of Education rolled out a series of mix modality of audio, visual and paper-based learning programmes. Accessing and benefitting from home-based distance learning modalities can be challenging for certain populations, leading to a risk of exacerbating already-existing disparities between students from different economic, geographic, and social groups. Findings from the recent Factsheet on Distance Learning conducted in June 2020 shown that the main barrier to accessing distance learning activities reported by caregivers and head teachers was accessing a television and that although schools are making some efforts to contact students, children without access to these technologies are likely to be at a disadvantage and more needs to be done to reach them.

# Methodology

3.1. Methodology overview

The assessment will utilize a two-stage research approach consisting of a secondary data review and primary data collection. A multi-faceted desk review and in-depth analysis of secondary sources, two distinct quantitative research components (structured household/individual interviews), and a series of in-depth qualitative engagements including focus group discussions with caregivers, children/youths (aged 12 to 24) and teachers, and key informant interviews with key educational stakeholders will be conducted.

An extensive secondary data review (SDR) will be conducted to develop a contextual understanding of developments within the Education Sector, particularly related to multi-year strategies focused on systems-building and improved access to high-quality educational opportunities. Primary data collection will consist of two surveys to obtain a holistic understanding of the recent response by the Education Sector and to collect statistically representative data on identified data gaps, complemented by in-depth qualitative information derived from group discussions with caregivers, children/youths and teachers and key informants with education authorities and committees.

Quantitative and qualitative data collection will take place between the 28th of September 2020 and the 9th of November 2020 comprising the following sample: structured interviews with 400 caregivers and 600 teachers/instructors, 20 FGDs with caregivers, children/youths (aged 12 to 24), and 20 KIIs with education experts.

3.2. Population of interest

In this assessment the populations of interest are refugee and HC children/youths between the ages of 3-24 in Ukhiya and Teknaf Upazilas, as well as caregivers and teachers providing education services to this population.

3.3. Secondary data analysis and review

Particular focus will be placed on conducting in-depth analysis of the results of the 2018 and 2019 Annual Status of Education Report (ASER) tests, with the 2018 serving as the “baseline” dataset conducted prior to the introduction of the LCFA in January 2019. Additionally, the findings from the in-depth analysis of ASER tests can be overlaid with other data sources, including ISCG Facility Mapping data on educational facilities, 5W data on educational activities and community engagement initiatives, or triangulated with Union-level findings from HC assessments in order to understand whether learning outcomes (as captured through the ASER tests) corroborate other assessment findings and data sources.

3.4. Primary Data Collection

Primary data collection will use a combination of 2 quantitative surveys, one conducted with caregivers and one with teachers and instructors in camps and in HC, 20 qualitative focus group discussions (FGDs) and 20 Key Informant Interviews (KIIs).

Due to the rapid spread of COVID-19, the specific risk to already vulnerable communities, the importance of the humanitarian principle of “Do No Harm” as well as general considerations for “Duty of Care” (i.e. ensuring both field staff and local communities are not spreading and/ or exposed to the risk of contracting COVID-19 due to data collection activities), IMPACT, with inputs and review support from WHO and Global Health Cluster colleagues, has developed a Standard Operating Procedures (SOPs) to guide research teams on how to undertake data collection during the COVID-19 outbreak. According to these SOPs, REACH’s team will assess the risks associated with data collection and decide the type of data collection as per the risk assessment in order to ensure safety of REACH staff, their families/communities and population in affected communities. Remote data collection such as phone interviews will be highly considered for quantitative surveys and KIIs.

In addition to standard training protocols, REACH will work with UNICEF and other partners to ensure that all staff involved in the research process receive adequate training from relevant specialists in the fields of psychological first aid, child safeguarding, prevention of sexual exploitation and abuse, and referral mechanisms.

Quantitative Surveys

For the quantitative data collection part of the assessment, two structured surveys have been developed. One will be used to conduct household interviews with Rohingya and Bangladeshi caregivers of children/youths aged 3-24,, while the second one will be used to conduct individual interviews with Bangladeshi teachers in HC and in camps and Burmese language instructors in camps. Both surveys will be conducted across camps and HC of Teknaf and Ukhyia upazilas, from October 15th to November 30th 2020.

The indicators to be included in each of the surveys will be guided by discussions with Education partners on prioritization and suitability of household-level questions. Data will be collected by teams of enumerators using a structured questionnaire administered at the household level with primary caregivers of children/youths aged 3-24, and with a randomly selected teachers or instructors. Data will be entered onto smartphones loaded with the Kobo app.

The caregivers’ surveys will be conducted among a total of 400 caregivers (100 Rohingya caregivers in camps in Ukhiya upazila, 100 Rohingya caregivers in camps in Teknaf upazila, 100 Bangladeshi caregivers in HC in Ukhiya upazila, 100 Bangladeshi caregivers in HC in Teknaf upazila) including a 5% buffer for quality data purposes (see Table 1). Sampling at the Upazila level will allow findings to be compared between Upazilas in an attempt to provide education actors with information to support strategic decision-making if and where results may vary significantly by locality. From both the refugee and HC Joint MSNAs from October 2019, gaps in household-reported access to educational opportunities seemed to be more pronounced in Teknaf Upazila. The current survey will therefore aim to collect data generalisable to the population of refugee and HC in each Upazila at 95% confidence level and 10% margin of error. For Rohingya caregivers, a stratified random sample approach of REACH/UNOSAT shelter footprints will be used, stratified by Upazila. For Bangladeshi caregivers, a random sampling of OpenStreetMap shelter footprints approach will be used.

The survey of teachers and instructors will be conducted among a total of 600 individuals (200 Bangladeshi teachers in camps, 200 Bangladeshi teachers in HC, 200 Burmese language instructors in camps) including a 5% buffer for quality data purposes. The questionnaire will focus on instructors’ perceptions and challenges related to implementing the LCFA (including but not limited to the extent of trainings and support materials received), and will also aim to collect information related to teacher recruitment, retention, and remuneration. In order to minimise the risk to data collectors and respondents with respect to COVID-19, this component will be done remotely through phone interviews, based on contact lists provided by the Education sector. If possible, depending on the provision of school and teacher contact lists provided by the Education Sector, a 2-stage random sampling will be used: the individual respondents will be randomly selected after the random sampling of the educational facilities. For each group, findings will be generalisable to the response level at a 95% confidence level and 10% margin of error.

The assessment team will be overseen by a Research Manager and Assessment Officer, and a Field Manager. Field teams will be led by a Field Coordinator with support from two Field Assistants. The Field Coordinator will manage 10 team leaders, 5 of whom will oversee 8 enumerators each, split evenly between males and females. The other 5 team leaders will oversee 8 security assistants (all male), who will partner with enumerators to minimise security risk/harassment.

Table 1: Sampling Framework for household surveys

| Upazila | Bangladeshi Population | Bangladeshi Samples | Rohingya Population | Rohingya Samples |
| --- | --- | --- | --- | --- |
| Total | 83,900 | 200 | 860,494 | 200 |
| Teknaf | 45,159 | 100 | 159,409 | 100 |
| Ukhiya | 37,940 | 100 | 701,085 | 100 |

Qualitative methods

FGDs and KIIs will focus on the effectiveness of the response, bottlenecks in the implementation of LCFA and equitable access to educational services, needs and barriers for marginalised children/youths such as girls, children/youths with disabilities or children/youths with non-binary gender identities. These components will also look at the learning opportunities affected by COVID-19.

Twenty Focus Group Discussions are planned to be conducted with the following groups: Bangladeshi caregivers, Rohingya caregivers, caregivers of children/youths with special needs, children/youths aged 12-24.

Twenty Key Informant Interviews will be conducted targeting the following key groups: CBOs supporting vulnerable or marginalised children/youths, Education NGO implementing partners and members of Learning Centre Management Committees.

Findings of the qualitative part of the assessment will contextualise and triangulate findings of quantitative data collection and SDR. To capitalise on the many specialist education organizations working within the Rohingya response, implementation of primary data collection tools could be a joint venture between REACH and interested Education Sector partners.

Final research design is subjected to an external ethical review in line with UNICEF’s procedure for ethical standards in research, evaluation, data collection and analysis. Given that REACH does not have a recognised institutional ethical review board (ERB) process, REACH will use the institutional review board of the Institute of Health Economics at the University of Dhaka.

Contingency plan due to COVID-19

If household data collection within camps or HC is restricted due to COVID-19 or other restrictions, REACH would plan to conduct a series of FGDs or KIIs to ensure the voices of households are represented. Similarly, if REACH is not able to conduct the planned FGDs in the camps or in the HC, KIIs could be remotely conducted.

3.5. Data Processing & Analysis

All identifying data will be stripped from databases/transcripts prior to analysis and publication. Databases containing potentially identifying data will be password protected with access limited to key staff. Informed consent of participants will be sought and received before the use of all research tools.

Data checking and cleaning of both household and education facility surveys will take place on a daily basis according to REACH’s data cleaning Minimum Standards Checklist. Each day REACH’s data team will conduct checks on the data and provide a list of issues and feedback to the field team. In addition, team leaders will continually monitor enumerator interview practices, providing feedback on an ad-hoc basis and during daily briefings. During data cleaning, checks will be made for outliers, “other” responses will be analysed and recoded as appropriate, incomplete or inaccurate records will be removed, and some responses may be recoded and standardised. All changes made to the original dataset will be recorded in a data cleaning log.

Data Analysis

Following the finalisation of tools, a data analysis plan for both qualitative and qualitative tools will be developed, ensuring linkages between questionnaire questions/responses, reporting on indicators, and stratification of the household sample. For the quantitative component, REACH will develop an analysis script using R software to conduct all of the analysis. For the FGDs and KIIs, notes or recordings will first be transcribed and translated into English, before being analysed thematically using QSR NVIVO software and input into a saturation grid.

Throughout the assessment process, IMPACT’s technical team in Geneva will conduct internal review and validation of tools and products in order to ensure they meet IMPACT’s organisational quality standards. This will take place prior to, and is subordinate to, final validation by the Sector.

Preliminary Findings Presentation and Final Outputs

Following data analysis, a preliminary findings presentation will be hosted by REACH to provide an overview of findings from all assessment components. This process will aim to encourage sector partners to reflect on the implications of the data, discuss findings that seem significant, surprising, and/or potentially contradictory across the various pieces of research, and to contextualize the findings based on their expertise and understanding of field realities. The key outcome of the workshop is an endorsed set of workshop minutes and assessment key messages, which will then feed into the development of final products.

Depending on the key findings and Sector-driven recommendations, the core outputs from this assessment would either take the form of a single full-length synthesized report, or can take the form of multiple analytical and thematic briefs accompanied by a synthesized executive summary to draw out key messages and common themes. The final decision will rest with the Sector and its advisory group (SAG), and should be decided with the goal of creating appropriate and effective assessment outputs for the intended audience of the Cox’s Bazar Education Sector, donors, the Global Education Cluster, and programmatic partners.

# 4. Workplan

|  | August |  |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  |  |  |  | January |  |  |  |  |  | February |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week: | 1 | 2 | 3 | 4 | 1 |  | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 | 1 |  | 2 | 3 | 4 | 5 | 1 |  | 2 |  | 3 | 4 | 5 | 1 |  | 2 |  | 3 | 4 |
| Inception and Kick-off | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOR development |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sector review and validation of ToR |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission of inception report |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Secondary analysis of ASER results and triangulation |  |  |  |  | X |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary presentation 1; Assessment Design Workshop |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quantitative tool development and piloting |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Qualitative tool development and piloting |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethnical clearance obtained |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and pilot of assessment teams |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quantitative data collection |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Qualitative data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary findings presentation 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Drafting of final outputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  | X | X | X | X |  | X |  |  |  |
| Review of products by sector partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |  |
| Final review of products by REACH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |
| Submission of final products |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

# 5. Roles and responsibilities

Table 2: Description of roles and responsibilities

| Task Description | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research design | Assessment Officer, Research Manager, GIS/Data Specialist, GIS Officer | Country Coordinator | IMPACT Research Design and Data Unit (RDDU) | UNICEF and Education Sector |
| Supervising data collection | Field Manager, Field Coordinator, Field Assistant, Team Leader | Country Coordinator | Assessment Officer, Research Manager , RDDU |  |
| Data processing (checking, cleaning) | Assessment Officer | Country Coordinator | Research Manager RDDU |  |
| Data analysis | Assessment Officer, Data Officer | Country Coordinator | Research Manager, GIS/Data Specialist RDDU |  |
| Output production | Assessment Officer | Country Coordinator | IMPACT Reporting Unit, Research Manager |  |
| Dissemination | Assessment Officer | Country Coordinator | IMPACT Communications Officer, Research Manager | UNICEF |
| Monitoring & Evaluation | Assessment Officer | Country Coordinator | IMPACT RDDU, Research Manager |  |
| Lessons learned | Assessment Officer | Country Coordinator | Country Coordinator, Research Manager RDDU | IMPACT HQ |

Responsible: the person(s) who executes the task

Accountable: the person who validates the completion of the task and is accountable of the final output or milestone

Consulted: the person(s) who must be consulted when the task is implemented

Informed: the person(s) who need to be informed when the task is completed

# 5. Data Management Plan

| Administrative Data |  |
| --- | --- |
| Research Cycle name | BGD2006 |
| Project Code | 70EAD |
| Donor | UNICEF |
| Project partners | Education Sector |

| Research Contacts | Patrick Sayers (patrick.sayers@reach-initiative.org) Helen Pittam (helen.pittam@reach-initiative.org) |  |
| --- | --- | --- |
| Data Management Plan Version | Date: 19/08/2020 | Version: 1.0 |

| Related Policies |  | IMPACT data protection SoPs IMPACT SoPs for data collection during Covid-19 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Documentation and Metadata |  |  |  |  |  |  |  |  |  |  |  |
| What documentation and metadata will accompany the data? Select all that apply |  | X | Data analysis plan |  |  |  | X |  | Data Cleaning Log, including: X Deletion Log X Value Change Log |  |  |  |
|  |  | X | Code book |  |  |  | X |  | Data Dictionary |  |  |  |
|  |  | □ | Metadata based on HDX Standards |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Ethics and Legal Compliance |  |  |  |  |  |  |  |  |  |  |  |
| Which ethical and legal measures will be taken? |  | X | Consent of participants to participate |  |  |  | □ |  | Consent of participants to share personal information with other agencies |  |  |  |
|  |  | □ | No collection of personally identifiable data will take place |  |  |  | X |  | Gender, child protection and other protection issues are taken into account |  |  |  |
|  |  | X | All participants reached age of majority |  |  |  |  |  | [Other, Specify] |  |  |  |
| Who will own the copyright and Intellectual Property Rights for the data that is collected? |  | IMPACT |  |  |  |  |  |  |  |  |  |
| Storage and Backup |  |  |  |  |  |  |  |  |  |  |  |
| Where will data be stored and backed up during the research? |  | X | IMPACT/REACH Kobo Server |  |  |  | □ |  | Other Kobo Server: [specify] |  |  |  |
|  |  | □ | IMPACT Global Physical / Cloud Server |  |  |  | □ |  | Country/Internal Server |  |  |  |
|  |  | □ | On devices held by REACH staff |  |  |  | □ |  | Physical location [specify] |  |  |  |
|  |  | □ | [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Which data access and security measures have been taken? |  | X | Password protection on devices/servers |  |  |  | X |  | Data access is limited to REACH staff |  |  |  |
|  |  | X | Form and data encryption on data collection server |  |  |  | □ |  | Partners signed an MoU if accessing raw data |  |  |  |
|  |  | □ | [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Kobo Access Rights |  |  |  |  |  |  |  |  |  |  |  |
| Kobo Access |  | Person |  |  |  | Account Name |  |  |  |  |  |
| View Form |  | Patrick Sayers, Tofajjel Hossein |  |  |  | reach_bgd |  |  |  |  |  |
| View and Edit Form |  | Patrick Sayers, Tofajjel Hossein |  |  |  | reach_bgd |  |  |  |  |  |
| View Form and Submit Data |  | Enumerators, Team Leaders. Field Coordinators |  |  |  | reach_bgd_enu2019 |  |  |  |  |  |
| Download Data |  | Patrick Sayers |  |  |  | zackarno_reach |  |  |  |  |  |
| Raw Data Access Rights |  |  |  |  |  |  |  |  |  |  |  |
| Raw Data Access |  | Reason |  |  |  | Person |  |  |  |  |  |
| Accountable |  | Accountable |  |  |  | Patrick Sayers |  |  |  |  |  |
| Access |  | Monitoring and data checking during assessment, data cleaning |  |  |  | Tofajjel Hossein |  |  |  |  |  |
| Access |  | Quality control and backstopping |  |  |  | Helen Pittam |  |  |  |  |  |
| Preservation |  |  |  |  |  |  |  |  |  |  |  |
| Where will data be stored for long-term preservation? |  | □ | IMPACT / REACH Global Cloud / Physical Server |  |  |  | □ |  | OCHA HDX |  |  |  |
|  |  | X | REACH Country Server |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Data Sharing |  |  |  |  |  |  |  |  |  |  |  |
| Will the data be shared publically? |  | X | Yes |  |  |  | □ |  | No, only with mandating agency / body |  |  |  |
| Will all data be shared? |  | X | Yes |  |  |  | □ |  | No, only anonymized, cleaned data will be shared |  |  |  |
|  |  | □ | No, [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Where will you share the data? |  | □ | REACH Resource Centre |  |  |  | □ |  | OCHA HDX |  |  |  |
|  |  | □ | HumanitarianResponse |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Data protection risk assessment |  |  |  |  |  |  |  |  |  |  |  |
| Have you completed the Indicators Risk Assessment table below? |  | X | Yes |  |  |  |  | □ | No, no information that potentially allows identification of individuals is to be collected. |  |  |
|  |  | [Please complete the first 4 columns in the Indicators Risk Assessment table below] |  |  |  |  |  |  |  |  |  |
| Risk indicator | Type of identification risk |  |  | Disclosure implications | Benefits |  |  |  |  | Class | Required mitigation |
| Key Informant job position and phone number | Direct contact/Identification of KI |  |  | Loss of privacy | Follow up for data cleaning, where need to verify/request additional information |  |  |  |  | B1 | Deleted directly after verification/cleaning |
| GPS points of sampled households | Data could be used identify the location of children/youths with specific vulnerabilities, |  |  | Targeting of vulnerable children/youths (for example, by trafficking groups) | GPS points critical to allow for monitoring of enumerator team adherence to sampling protocols and will be deleted after data checking |  |  |  |  | B1 | To be deleted once analysis and any necessary mapping have been completed, and before sharing any version of the dataset. |
| Responsibilities |  |  |  |  |  |  |  |  |  |  |  |
| Data collection |  | Patrick Sayers, Research Manager, patrick.sayers@reach-initiative.org |  |  |  |  |  |  |  |  |  |
| Data cleaning |  | Zack Arno, GIS Specialist, zack.arno@reach-initiative.org |  |  |  |  |  |  |  |  |  |
| Data analysis |  | Patrick Sayers and Zack Arno |  |  |  |  |  |  |  |  |  |
| Data sharing/uploading |  | Patrick Sayers |  |  |  |  |  |  |  |  |  |

Upazila is the 3rd level of administrative subdivisions in Bangladesh, it corresponds to sub-districts. Bangladesh has 4 main administrative subdivisions’ level: Divisions, Districts, Upazilas, Unions.

This will include a 5% buffer for data quality purposes.

UNHCR population data and key demographic indicators. September 30, 2019

Cox’s Bazar Education Sector. Joint Education Needs Assessment: Rohingya Refugee in Cox’s Bazar, June 2018, p. 4.

Education Cannot Wait Facilitated Multi-Year Reslience Programme, 2018-2020, p. 7

REACH / ISCG. Joint Multi-Sector Needs Assessment: Host Communities in Ukhiya and Teknaf. Analysis Tables. October 2019

Cox’s Bazar Education Sector. 5Ws. September 2019. The estimated 5,000 facilities are inclusive of learning centres, mobile learning, home-based learning, and other types of facilities

REACH / Cox’s Bazar Education Sector. Education Needs Assessment. March 2019.

Human Rights Watch. “Are We Not Human?” Denial of Education for Rohingya Refugee Children in Bangladesh. December 2019

The LCFA has been introduced by the Education Sector in 2018 within the camps as an alternative education curriculum, outlining a set of learning competencies across four developmental levels equivalency from pre-primary to grade eight (levels I-IV), covering English, Myanmar language, Mathematics, Life Skills and Science.

REACH. COVID-19 Distance Learning in Cox's Bazar District: Host Communities in 8 upazilas. June 2020